## Test Plan
Please click here for EonBazar testplan full PDF.

## Mind Maps
Mind Map of Eonbazar Web Application

## TestScenarios
Project Name | Eonbazar
Reference Document | FRS
Created By | Mamun Ali
Creation Date | 2025-05-05
Approval Date | 28/5/2025
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the user Registration | P0 | 8
TS_002 |  | Validate the user Login | P0 | 17
TS_003 |  | Validate the user logout | P0 | 5
TS_004 |  | Validate the forgot password | P1 | 15
TS_005 |  | Validate the social login | P1 | 12
TS_006 |  | Validate the user add product to shopping Cart | P1 | 12
TS_007 |  | Validate the user checkout any product | P1 | 10
TS_008 |  | Validate Responsive Design & Compatibility | P3 | 5
TS_009 |  | Validate Product Categorization | P1 | 11
TS_010 |  | Validate the category functionality | P2 | 10
TS_011 |  | Validate website compatibility across multiple browsers. | P4 | 3

## TestCase
Product Name |  | Eonbazar | TC Start Date | 2025-05-05 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  |  | TC End Date | 28/5/2025 | TC Execution End Date | - - |  |  |  |  | PASS | 58
Epic |  |  | Test Case Developed By | Mamun Ali | Browser (tested) | Yes |  |  |  |  | FAIL | 27
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  |  | NO RUN | 7
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 92
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Status | Remarks
1 | User Registration |  | Registration | Register with valid details | User is redirected to dashboard/home with a success message. Email/OTP verification may be required. | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Passed
2 |  |  |  | Register using an already registered email | Error message shown: “Email already exists” | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Passed
3 |  |  |  | Register with an incorrectly formatted email | Error: “Please enter a valid email address” | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Passed
4 |  |  |  | Register with a weak password (e.g., "123") | Error message or password strength indicator suggests using a stronger password | Not Found as per expectation. | None | 1. Fill out all valid fields. 2.Use a short/weak password |  |  | Failed
5 |  |  |  | Attempt to register without filling mandatory fields | Display required field warnings (e.g., "This field is required") | Not Found as per expectation. | None | 1. Leave one or more fields blank (e.g., email, password) 1. Click register |  |  | Failed
6 |  |  |  | Missing Required Fields | Display required register button is disabled (e.g., "This field is required") | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Passed
7 |  |  |  | Enter an incorrect or too short phone number | Error shown: “Enter a valid phone number” | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4. Click on "login" button |  |  | Passed
8 |  |  |  | Missing Required Fields with lebel error message | Missing any any fields to show the error message down input field | Not Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Failed
9 |  |  | Logout | Verify Successful Logout | User is logged out and redirected to the login or homepage. | Found as per expectation. | None | Log in with valid credentials → Click on the "Logout" button. |  |  | Passed
10 |  |  |  | Verify Session Termination | Access is denied; user is prompted to log in again. | Not Found as per expectation. | None | Log in → Click "Logout" → Attempt to access a restricted page via browser history. |  |  | Failed
11 |  |  |  | Verify Logout from Multiple Devices | Session on Device B remains active (unless single-session enforcement is implemented) | Not Found as per expectation. | None | Log in on Device A and Device B → Log out from Device A. |  |  | Failed
12 |  |  |  | Verify Logout Without Active Session | User is redirected to the login page or shown an appropriate message. | Found as per expectation. | None | Access the logout URL directly without logging in. |  |  | Passed
13 |  |  |  | Verify Multiple Logout Attempts | System handles repeated requests gracefully without errors. | Found as per expectation. |  | Click "Logout" multiple times rapidly. |  |  | Passed
14 | User Login |  | Login | Ensure that both email and password fields are mandatory. | Error messages are displayed for both fields. | Not Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Click on the Register button |  |  | Failed
15 |  |  |  | Verify that the system handles invalid login attempts gracefully. | An error message indicating invalid credentials is displayed. | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Click on the Register button |  |  | Passed
16 |  |  |  | Verify multiple login attempts in a row. | It will not reject or give an error message if you make multiple login attempts in a row. | Not Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter password with length less than 5 4. Accept the terms and conditions 5. Click Register button |  |  | Failed
17 |  |  |  | Verify that a user can login successfully with valid phone number. | User is successfully logged in and redirected to dashboard/homepage | Found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter password with length more than 5. |  |  | Passed
18 |  |  |  | Verify login with invalid number | Error message shown: “Invalid credentials” | Found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter password with length more than 5. 4. Re-enter password to confirm 5. Accept the terms and conditions 6. Click Register button |  |  | Passed
19 |  |  |  | Verify OTP button disabled/enabled state | Button disabled until all required fields are filled | Not found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter password with length less than 5. 4. Re-enter password to confirm 5. Checking the terms and conditions |  |  | Failed
20 |  |  |  | Check login rate limiting or CAPTCHA | Account locked or CAPTCHA triggered. | Not found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter Invalid email 4. Enter password with length more than 5. 5. Re-enter password to confirm 6. Accept the terms and conditions 7. Click Register button |  |  | Failed
21 |  |  |  | Verify login with valid credentials | User is successfully logged in and redirected to dashboard/homepage | Found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Skip the email 4. Enter password with length more than 5 5. Re-enter password to confirm 6. Accept the terms and conditions 7. Click Register button |  |  | Passed
22 |  |  |  | Verify login with invalid password | Error message shown: “Invalid credentials” | Found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter valid email 4. Enter password with length more than 5 5. Re-enter password to confirm 6. Checking the terms and conditions 7. Click Register button |  |  | Passed
23 |  |  |  | Verify login with invalid email | Error message shown: “Invalid credentials” | Found as per expectation. | adritaalam.prima+1@gmail.com | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter email that is already used using +1 with the email 4. Enter password with length more than 5 5. Re-enter password to confirm 6. Checking the terms and conditions 7. Click Register button |  |  | Passed
24 |  |  |  | Verify login with empty email field | Validation message: “Email is required” | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter email that is already used 4. Enter password with length more than 5 5. Re-enter password to confirm 6. Accept the terms and conditions 7. Click Register button |  |  | Passed
25 |  |  |  | Verify “Forgot Password” link | User is redirected to reset password page | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter valid email 4. Enter password with length more than 5 5. Re-enter password to confirm 6. Accept the terms and conditions 7. Click Register button 8. Checking gmail inbox |  |  | Passed
26 |  |  |  | Verify email field format validation | Error shown: “Invalid email format” | Found as per expectation. | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the Signup button in the right corner. 3. Enter valid email 4. Enter password with length more than 5 5. Re-enter password to confirm 6. Accept the terms and conditions 7. Click Register button 8. Checking gmail spam section |  |  | Passed
27 |  |  |  | Check "Show Password" functionality | Password should become visible after clicking eye icon | Not found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click password field and type password. 3. visible field right side eye icon for show password. 4. Click eye icon then show password. |  |  | Failed
28 |  |  |  | Verify logout close browser | Browser close and reopen without logout stayed loged in | Found as per expectation |  | 1. Go to the URL https://eonbazar.com/auth/signin 2. Close ther browser. 3. Reopen the browser. 4. Check the user login condition. |  |  | Passed
29 |  |  |  | Verify login button disabled/enabled state | Button disabled until all required fields are filled | Not found as per expectation |  | 1. Go to the URL https://eonbazar.com/auth/signin 2. Click on the "Login" button in the top right corner. 3. Observe the "Login" button in the modal or login form. 4. Leave both username and password fields empty. 5. Enter only the username. 6. Clear the username and enter only the password. 7. Enter both correct username and password. |  |  | Failed
30 |  |  |  | Verify redirection to signup page | Redirects to signup page | Not found as per expectation | None | 1. Go to the URL https://eonbazar.com/auth/signin 2. On the login form, locate and click the "Sign up" link or button (usually labeled “Don't have an account? Sign up”). 3. Observe the URL and page content after clicking. |  |  | Failed
31 | User Forgot Password |  | Forget password | Verify 'Forgot Password' Link Visibility | "Forgot Password" link is visible on the login page. | Found as per expectation | None | 1. Open the EonBazar login page. 2. Observe the UI for a "Forgot Password" link. |  |  | Passed
32 |  |  |  | Verify 'Forgot Password' Link Redirection | Clicking the link redirects to the password reset request page. | Found as per expectation | None | 1.Click on the "Forgot Password" link on the login page. 2.Confirm redirection to a password reset form. |  |  | Passed
33 |  |  |  | Verifying Submit Registered Email | A success message is shown; reset link is sent to the email. | Found as per expectation |  | 1. Go to the "Forgot Password" page. 2. Enter a valid registered email. 3. Click "Submit" or "Reset Password". 4. Check for confirmation message or email notification. |  |  | Passed
34 |  |  |  | Verifying Submit Unregistered Email | An error message is displayed like "Email not found". | Found as per expectation | None | 1. Go to the "Forgot Password" page. 2. Enter an unregistered email. 3. Click "Submit". 4. Observe the system response. |  |  | Passed
35 |  |  |  | Verifying Submit Empty Email Field | Validation error is shown: “Email field cannot be empty”. | Found as per expectation | None | 1. Navigate to the "Forgot Password" page. 2. Leave the email field blank. 3. Click "Submit". |  |  | Passed
36 |  |  |  | Verifying Email Format Validation | An error like "Invalid email format" appears. | Found as per expectation | None | 1. Enter an invalid email (e.g., "user@com"). 2. Click "Submit". |  |  | Passed
37 |  |  |  | Verifying reset password with phone number | A success message is shown; reset password with phone number and redirect reset password page | Not Found as per expectation | None | 1. Enter phone number reset password field. 2. Click "Submit". |  |  | Failed
38 |  |  |  | Verifying Check Email Receipt | The user receives a password reset email with a link. |  |  | 1. Submit a valid email. 2. Check the inbox (and spam folder). 3. Confirm presence of a reset email. |  |  | Not Executed
39 |  |  |  | Verifying Reset Link Opens Reset Page | Clicking the email link redirects to a secure password reset page. |  |  | 1. Open the reset email. 2. Click the reset link. 3. Ensure the browser redirects to the reset password form. |  |  | Not Executed
40 |  |  |  | Verifying Successful Password Reset | Password is updated and success message is shown. |  |  | 1. Open reset link. 2. Enter a new valid password and confirm it. 3. Submit the form. |  |  | Not Executed
41 |  |  |  | Verifying Mismatched Passwords | Error shown: "Passwords do not match". |  |  | 1. Enter different values in "New Password" and "Confirm Password" fields. 2. Submit the form. |  |  | Not Executed
42 |  |  |  | Verifying Weak Password Handling | Error shown if password does not meet strength criteria. |  |  | 1. Enter a weak password (e.g., "123"). 2. Submit the form. |  |  | Failed
43 |  |  |  | Verifying Login with New Password | User is able to log in using the new password. |  |  | 1. Complete the password reset process. 2. Navigate to login page. 3. Log in with the new password. |  |  | Not Executed
44 |  |  |  | Verifying Reuse of Reset Link | The link should be expired after use; error message displayed. |  |  | 1. Use a reset link once. 2. Try to use it again after the password is already changed. |  |  | Not Executed
45 |  |  |  | Verifying Expired Reset Link | System shows “Link expired” message. |  |  | 1. se a reset link after its expiry period (e.g., after 1 hour). 2. Try submitting a new password. |  |  | Not Executed
47 | User login into Social media |  | Social Login | Verify Social Login Buttons Visibility | Social login buttons (e.g., "Continue with Google") are visible on the login page. | Found as per expectation | None | 1. Navigate to the EonBazar login page. 2. Look for available social login options. |  |  | Passed
48 |  |  |  | Verify Redirection to Social Platform Google | Clicking the social login button redirects to the respective platform’s authentication page (e.g., Google login screen). | Found as per expectation | None | 1. Click on the Google login button. 2. Confirm redirection to the correct external login page. |  |  | Passed
49 |  |  |  | Verify Redirection to Social Platform Facebook | Clicking the social login button redirects to the respective platform’s authentication page (e.g., Google login screen). | Not Found as per expectation | None | 1. Click on the Facebook login button. 1. Confirm redirection to the correct external login page. |  |  | Failed
50 |  |  |  | Verifying Successful Login with Social Account (Google) | User is logged in and redirected to the website/dashboard. | Found as per expectation | None | 1. Click on a social login button. 2. Enter valid credentials on the social provider's page. 3. Allow necessary permissions. 4. Confirm redirection to user dashboard. |  |  | Passed
51 |  |  |  | Verifying Successful Login with Social Account (Facebook) | User is logged in and redirected to the website/dashboard. | Not Found as per expectation | None | 1. Click on a social login button. 2. Enter valid credentials on the social provider's page. 3. Allow necessary permissions. 4. Confirm redirection to user dashboard. |  |  | Failed
52 |  |  |  | Verifying Cancel Authentication on Social Platform | User is redirected back to login page with an appropriate message. | Found as per expectation |  | 1. Click the social login button. 2. On the provider’s login screen, click cancel or close the popup. 3. Confirm you are returned to the original login screen. |  |  | Passed
53 |  |  |  | Verifying First-Time Social Login | User account is created and logged in if it doesn't already exist. |  |  | 1. Use a social account that hasn’t been used before. 2. Complete authentication. 3. Verify account creation and redirection. |  |  | Passed
54 |  |  |  | Verifying Deny Permission on Social Platform | Login should fail and redirect with an appropriate error message. |  |  | 1. Click the social login button. 2. Deny access when prompted by the provider. 2. Confirm error is displayed on return. |  |  | Passed
55 |  |  |  | Verifying Verify Token Handling (Security) | Access token must be stored securely and used for session handling. |  |  | 1. Log in via social login. 2. Inspect browser storage or use developer tools. 3. Ensure token is not exposed in URLs or local storage (if security-critical). |  |  | Failed
56 |  |  |  | Verifying Social Login Button Functionality on Mobile | Buttons must work properly on mobile devices. |  |  | 1. Open the site on a mobile browser. 2. Tap the social login button. 3. Confirm redirection and authentication. |  |  | Passed
57 |  |  |  | Verifying Logout After Social Login | User should be logged out from the application, but not necessarily from the social provider. |  |  | 1. Login using a social account. 2. Click logout. 3. Confirm redirection to login page and token/session termination. |  |  | Failed
58 |  |  |  | Verifying Re-login After Social Logout | Re-clicking the social login button should log the user in again without entering credentials (if session on provider is active). |  |  | 1. Login via Google/Facebook. 2. Logout from the website only. 3. Click login with social again. 4. Confirm auto-login if still logged into the social account. |  |  | Passed
59 | User add to cart to product list |  | Add to cart | Verifying Add Product from Product Listing Page | Product is added to the cart; confirmation is shown (e.g., "Added to Cart"). | Found as per expectation | None | 1. Go to a product listing/category page. 2. Click the "Add to Cart" button on any product. 3. Check cart icon or cart page for the item. |  |  | Passed
60 |  |  |  | Verifying Add Product from Product Details Page. | Product is added to the cart; user gets confirmation. | Found as per expectation | None | 1. Open a specific product detail page. 2. Click "Add to Cart". 3. Verify the product is added. |  |  | Passed
61 |  |  |  | Verifying Add Same Product Multiple Times | Quantity of the product in the cart increases accordingly. | Found as per expectation | None | 1. Add a product to cart. 2. Add the same product again. 3. Check if the quantity is updated (e.g., 2 items). |  |  | Passed
62 |  |  |  | Verifying Add Out-of-Stock Product | Product cannot be added; user is notified it’s out of stock. | Found as per expectation | None | 1. Find an out-of-stock product. 2. Click "Add to Cart". 3. Observe system response. |  |  | Passed
63 |  |  |  | Verifying Cart Icon/Counter Updates Correctly | Cart icon counter shows correct item count after adding product. | Found as per expectation | None | 1. Add one or more products. 2. Observe the cart icon in the header or navbar. |  |  | Passed
64 |  |  |  | Verifying Cart Persists After Page Refresh | Items remain in the cart after reloading the page. | Found as per expectation | None | 1. Add a product to cart. 2. Refresh the page. 3. Open cart and confirm item is still present. |  |  | Passed
65 |  |  |  | Verifying Add Product While Not Logged In | Product is added to a guest session cart. | Not Found as per expectation | None | 1. Log out of the account (if logged in). 2. Add product to cart. 3. View cart and confirm presence. |  |  | Failed
66 |  |  |  | Verifying Add Product with Maximum Quantity Limit | System prevents user from exceeding max quantity (e.g., 10 items). | Not Found as per expectation | None | 1. Open product detail page. 2. Try adding quantity beyond the limit. 3. Check for error or warning message. |  |  | Failed
67 |  |  |  | Verifying Cart Session Persists After Login | Items added while logged out are retained after user logs in. | Found as per expectation | None | 1. As guest, add items to cart. 2. Log into your account. 3. Check if those items still appear in the cart. |  |  | Passed
68 |  |  |  | Verifying Add Product via Quick View Modal | Product is added from popup modal without opening full product page. | Found as per expectation | None | 1. Click "Quick View" on a product. 2. Click "Add to Cart" in modal. 3. Verify addition in cart. |  |  | Passed
69 |  |  |  | Verifying Error Handling on Failed Add (Network Issue) | An error message is shown, and item is not added. | Found as per expectation | None | 1. Disable internet or simulate network failure. 2. Try adding product. 3. Confirm error message and cart status. |  |  | Passed
71 | USer checkout product |  | Product Checkout | Verifying Initiate Checkout from Shopping Cart | User is redirected to the checkout page with all selected items correctly listed. | Found as per expectation | None | 1. Navigate to EonBazar's shop page. 2. Add multiple items to the shopping cart. 3. Click on the cart icon and select "Proceed to Checkout." |  |  | Passed
72 |  |  |  | Verifying Registered User Checkout Process | Registered users can log in, and their saved information auto-populates during checkout. | Found as per expectation | None | 1. Log in with valid credentials. 2. Add an item to the cart. 3. Proceed to checkout and verify that shipping and payment details are pre-filled. 4. Confirm and place the order. |  |  | Passed
73 |  |  |  | Verifying User Ordered Prooduct Cancel | If the user wants to cancel an order after ordering a product, they will click on the cancel button and the order will be canceled. | Found as per expectation | None | 1. Log in with valid credentials. 2. Add an item to the cart. 3. Proceed to checkout and verify that shipping and payment details are pre-filled. 4. Confirm and place the order. 5. Confirm the order then click Cancel order button. |  |  | Failed
74 |  |  |  | Verifying Guest Checkout Process | Guest users can complete the checkout without account creation, providing necessary shipping and payment information. | Not Found as per expectation | None | 1. Add an item to the cart. 2. Proceed to checkout without logging in. 3. Fill in shipping and payment details. 4. Confirm and place the order. |  |  | Failed
75 |  |  |  | Verifying Payment Gateway Functionality | Users can select a payment method, enter details, and receive confirmation upon successful payment. | Found as per expectation | None | 1. Proceed to checkout with items in the cart. 2. Select a payment method (e.g., credit card, mobile payment). 3. Enter valid payment details. 4. Submit payment and verify confirmation message. |  |  | Passed
76 |  |  |  | Verifying Order With Cash On Delivery | Users can select cash on delivery, enter details, and receive confirmation and successful order placed. | Found as per expectation | None | 1. Proceed to checkout with items in the cart. 2. Select Cash on Delivery. 3. Enter valid payment details. 4. Submit payment and successfully order placed. |  |  | Passed
77 |  |  |  | Verifying Order Confirmation Email | User receives an order confirmation email with order details after successful checkout. | Not Found as per expectation | None | 1. Complete a purchase as a registered or guest user. 2. Check the provided email inbox for a confirmation message. |  |  | Failed
78 |  |  |  | Verifying Product Detail Page Accuracy | Product pages display correct information, including name, description, price, and images. | Found as per expectation | None | 1. Navigate to a product page, such as Chocolate Almond Cookies. 2. Verify that all product details are accurate and images are displayed properly. |  |  | Passed
79 |  |  |  | Verifying Order Confirmation Phone number message | User receives an order confirmation message in phone with order details after successful checkout. | Found as per expectation | None | 1. Complete a purchase as a registered or guest user. 2. Check the provided Phone number for a confirmation message |  |  | Passed
80 |  |  |  | Verifying Product Dont Oder Without Address | User dont order product without confirmed address section. | Found as per expectation | None | 1. Proceed to checkout with items in the cart. 2. Select address. 3. Enter address details. 4. Submit payment and verify confirmation message. |  |  | Passed
81 | Filter Product |  | Filter Product | Verifying Filter Products by Category. | Only products from the selected category are displayed. | Found as per expectations | None | 1. Go to https://eonbazar.com/shop. 2. From the sidebar or menu, click on a product category (e.g., “Bakery,” “Meat,” or “Frozen”). 3. Observe the product listing area. 4. Ensure only products from the selected category are shown. |  |  | Passed
82 |  |  |  | Verifying Filter by Price Range. | Only products within the selected price range are shown. | Found as per expectations | None | 1. Navigate to the Shop page. 2. Use the price range slider (if available) to select a range (e.g., 200–500 BDT). 3. Click "Filter" or wait for automatic update. 4. Confirm that all displayed products fall within the chosen price range. |  |  | Passed
83 |  |  |  | Verifying Filter by Tag or Attribute (e.g., “Frozen”, “Organic”) | Products with the selected tag/attribute are displayed. | Found as per expectations | None | 1. On the sidebar, locate the “Tags” or “Attributes” section (e.g., “Frozen,” “Antibiotic-free”). 2. Click on one of the tags. 3. Verify the listed products have that specific tag/attribute. |  |  | Passed
84 |  |  |  | Verifying Filter by (Rating high to low & low to high) | Products with the Rating High to low & low to high are displayed. | Not found as per expectation | None | 1. On the sidebar, locate the “Tags” or “Attributes” section (e.g., “Frozen,” “Antibiotic-free”). 2. Click on one of the Rating hight to low or low to high. 3. Verify the listed products have that specific tag/attribute. |  |  | Failed
85 |  |  |  | Verifying Apply Multiple Filters Together. | Product list updates to show only items that match all selected filters. | Found as per expectations | None | 1. Select a category (e.g., “Meat”). 2. Select a price range (e.g., 200–600 BDT). 3. (Optional) Select a tag or brand. 4. Confirm that only products matching all filters are displayed. |  |  | Passed
86 |  |  |  | Verifying Clear All Filters. | All applied filters are removed and the full product list is shown again. | Found as per expectations | None | 1. Apply one or more filters. 2. Click the “Clear All” button or manually deselect each filter. 3. Observe that the product list returns to its original full state. |  |  | Passed
87 |  |  |  | Verifying Filter Retention After Page Refresh. | Filters should reset (or persist, based on design), but behavior must be consistent. | Found as per expectations | None | 1. Apply any filter (e.g., category or price). 2. Refresh the page. 3. Observe whether filters reset or are retained (as per site logic). 4. Confirm expected behavior matches implementation. |  |  | Passed
88 |  |  |  | Verifying Filter Result Accuracy. | No unrelated or incorrect products are shown in filtered results. | Found as per expectations | None | 1. Select a very specific filter (e.g., "Frozen Snacks"). 2. Review all the products listed. 3. Verify that none of them fall outside the selected criteria. |  |  | Passed
89 |  |  |  | Verifying No Products Matching Filter. | Message like “No products found” should appear when no items match. | Found as per expectations | None | 1. Apply a very narrow combination of filters (e.g., a low price + rare tag). 2. Check if the site displays a proper message and doesn’t break layout or crash. |  |  | Passed
90 |  |  |  | Verifying Mobile Filter Usability. | Filter options should be accessible and functional on mobile devices. | Found as per expectations | None | 1. Open the website on a mobile device. 2. Navigate to the shop page. 3. Try applying filters from the mobile sidebar or menu. 4. Confirm that filtering works as expected and interface remains responsive. |  |  | Passed
91 |  |  |  | Verifying Filter UI Responsiveness. | Filter elements (dropdowns, sliders, checkboxes) respond quickly without delay or UI glitches. | Found as per expectations | None | 1. Use various filters (click, slide, deselect). 2. Observe response time and animations. 3. Ensure no lag, flickering, or visual bugs. |  |  | Passed
92 | Product Category |  | Product Category | Verifying Category List Loads Properly | All available categories are listed correctly on the homepage or shop sidebar. | Found as per expectations | None | 1. Visit https://eonbazar.com. 2. Scroll to the sidebar or homepage category section. 3. Verify that all intended categories (e.g., Meat, Dairy, Bakery, Snacks) are visible and clickable. |  |  | Passed
93 |  |  |  | Verifying Category Page Displays Relevant Products | When clicking a category, only products that belong to that category are shown. | Found as per expectations | None | 1. Click on a category like "Bakery" or "Frozen." 2. Review the products displayed. 3. Ensure each product is related to that category. |  |  | Passed
94 |  |  |  | Verifying Category Breadcrumb Navigation | Breadcrumb (e.g., Home > Bakery) appears at the top of the category page for navigation. | Found as per expectations | None | 1. Open a specific category. 2. Check the top of the page for breadcrumb navigation. 3. Verify that clicking “Home” or higher levels redirects appropriately. |  |  | Passed
95 |  |  |  | Verifying Empty Category Handling | A user-friendly message appears if a category has no products (e.g., “No products found”). | Found as per expectations | None | 1. Go to a category that has no items (if any). 2. Confirm a proper message is shown instead of an empty layout or error. |  |  | Passed
96 |  |  |  | Verifying Pagination Within a Category | Products within a category are paginated correctly if there are more items than fit one page. | Not Found as per expectations | None | 1. Go to a category with many products (if available). 2. Scroll down and click page 2. 3. Ensure additional products load correctly and remain within that category. |  |  | Failed
97 |  |  |  | Verifying Category Selection from Menu (Header or Mobile Nav) | Clicking on a category from the header or mobile menu redirects to the appropriate category page. | Found as per expectations | None | 1. Click the main menu or hamburger icon on mobile. 2. Select any category. 3. Confirm redirection and relevant products are displayed. |  |  | Passed
98 |  |  |  | Verifying Subcategory Display | Subcategories (if any) should be shown under parent categories and functional. | Found as per expectations | None | 1. Navigate to a main category. 2. Look for subcategories (e.g., under "Meat" there might be “Chicken,” “Beef”). 3. Click on a subcategory and ensure proper filtering. |  |  | Passed
99 |  |  |  | Verifying Category Image or Banner | A relevant image or banner appears on the top of the category page. | Found as per expectations | None | 1. Open a category page. 2. Check for a featured image/banner and verify it fits the category theme. |  |  | Passed
100 |  |  |  | Verifying Responsive Category Access | Categories can be accessed and used from mobile devices with correct touch response and layout. | Found as per expectations | None | 1. Open the site on a mobile device. 2. Tap the hamburger menu and go to any category. 3. Confirm navigation and category listing is smooth and readable. |  |  | Passed
101 |  |  |  | Verifying Category Page Title and URL | The browser title and URL reflect the selected category. | Found as per expectations | None | 1. Open any category (e.g., “Frozen”). 2. Observe the page title (e.g., “Frozen Products – EonBazar”). 3. Check that the URL changes to something like /product-category/frozen/. |  |  | Passed
102 | Responsive Design & Compatibility |  | Responsiveness | Verifying Ensure homepage layout adapts to different screen sizes. | 1. Layout adapts fluidly without horizontal scroll. 2. No content overlaps or breaks. 3. Text and buttons remain readable.. | Not Found as per expectations | None | 1. Open browser developer tools (F12). 2. Switch to device toolbar (toggle responsive mode). 3. Select screen sizes: 4. 320x480 (Mobile) 5. 768x1024 (Tablet) 6. 1366x768 (Desktop) 7. Reload the page on each size. | https://prnt.sc/YC8QJae25Qyu |  | Failed
103 |  |  |  | Verifying Test navigation bar behavior on smaller screens. | 1.Navigation collapses into a hamburger icon. 2. Menu expands when tapped. 3. Links are accessible and clickable. | Found as per expectations | None | 1. Resize browser to < 768px width or open the site on a mobile device. 2. Tap the hamburger icon. |  |  | Passed
104 |  |  |  | Verifying Check image responsiveness and alignment. | 1. Images resize proportionally. 2. No image cropping, distortion, or pixelation. | Found as per expectations | None | 1. Visit homepage and product pages. 2. Resize screen from desktop to mobile width gradually. |  |  | Passed
105 |  |  |  | Verifying that buttons are large enough on mobile. | 1. Interactive elements are at least 48x48dp. 2. Easy to tap without precision. | Found as per expectations | None | 1. Open site on a mobile device. 2. Tap on buttons, dropdowns, and product cards. |  |  | Passed
106 |  |  |  | Verifying layout adapts to portrait and landscape. | 1. Layout readjusts properly. 2. No elements are cut off or misaligned. | Not Found as per expectations | None | 1. Open on a mobile or tablet. 2. Switch between portrait and landscape. | https://prnt.sc/SpdlyvsbP7Kl |  | Failed
107 | Compatibility Test |  | Browser Compatibility | Verifying Ensure consistent rendering on major browsers. | 1. No layout breaking. 2. JS and CSS load correctly. 3. Fonts and colors display uniformly. | Found as per expectations | None | 1. Open site on: 2. Google Chrome 3. Mozilla Firefox 4. Safari 5. Microsoft Edge 6. Browse homepage and product pages. |  |  | Passed
108 |  |  |  | Verifying Test on various operating systems. | 1. Site behaves consistently across OS. 2. No feature is OS-specific or broken. | Found as per expectations | None | 1. Open site on: 2. Windows (Chrome, Edge) 3. macOS (Safari, Chrome) 4. Android (Chrome) 5. iOS (Safari) |  |  | Passed
109 |  |  |  | Verifying Test on real or emulated devices. | 1. Fully functional and visually consistent. 2. No missing content or UI bugs. | Found as per expectations | None | 1. Access website on: • Android Phone • iPhone • iPad • Windows Laptop • MacBook 2. Navigate through major sections. |  |  | Passed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Bug Report
Bug Reporting
#SL 01
Issue: Register with a weak password (e.g., "123") not indicate.
Reproducing Steps:
1. Goto the URL https://eonbazar.com/auth/signin
2. Fill out all valid fields.
3. Use a short/weak password
Env:
Module: Signup
Priority: P0
Severity: Major
Screenshot:
Expected: Error message or password strength indicator suggests using a stronger password
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 02
Issue: Attempt to register without filling mandatory fields
Reproducing Steps:
1. Goto the URL https://eonbazar.com/auth/signin
2. Leave one or more fields blank (e.g., email, password)
3. Click register
Env:
Module: Signup
Priority: P0
Severity: Major
Screenshot:
Expected: Display required field warnings (e.g., "This field is required").
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 03
Issue: Missing Required Fields with lebel error message.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the "Login" button in the right corner.
3. Enter correct credentials
4. Click on "login" button
Env: Production
Module: Signup
Priority: P1
Severity: Major
Screenshot:
Expected: Missing any any fields to show the error message down input field.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 04
Issue: Verify Session Termination
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Log in
3. Click "Logout"
4. Attempt to access a restricted page via browser history.
Env: Production
Module: Logout
Priority: P0
Severity: Major
Screenshot:
Expected: Access is denied; user is prompted to log in again.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 05
Issue: Verify Logout from Multiple Devices.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Log in on Device A and Device B
3. Log out from Device A.
Env: Production
Module: Logout
Priority: P0
Severity: Major
Screenshot:
Expected: Session on Device B remains active (unless single-session enforcement is implemented).
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 06
Issue: Ensure that both email and password fields are mandatory.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the Signup button in the right corner.
3. Click on the Register button
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Error messages are displayed for both fields.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 07
Issue: You can take multiple login attempts in a row.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the Signup button in the right corner.
3. Enter password with length less than 5
4. Accept the terms and conditions
5. Click Register button
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: It will not reject or give an error message if you make multiple login attempts in a row.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 08
Issue: Verify OTP button disabled/enabled state.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the Signup button in the right corner. 3. Enter Invalid email 4. Enter password with length more than 5. 5. Re-enter password to confirm 6. Accept the terms and conditions 7. Click Register button
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Error messages are displayed for both fields.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 09
Issue: Verify OTP button disabled/enabled state.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the Signup button in the right corner.
3. Enter password with length less than 5.
4. Re-enter password to confirm
5. Checking the terms and conditions
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Button disabled until all required fields are filled.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 10
Issue: Check login rate limiting or CAPTCHA.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the Signup button in the right corner.
3. Enter Invalid email
4. Enter password with length more than 5.
5. Re-enter password to confirm
6. Accept the terms and conditions
7. Click Register button
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Account locked or CAPTCHA triggered.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 11
Issue: Check "Show Password" functionality.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click password field and type password.
3. visible field right side eye icon for show password.
4. Click eye icon then show password.
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Error messages are displayed for both fields.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 12
Issue: Verify login button disabled/enabled state.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the "Login" button in the top right corner.
3. Observe the "Login" button in the modal or login form.
4. Leave both username and password fields empty.
5. Enter only the username.
6. Clear the username and enter only the password.
7. Enter both correct username and password.
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Button disabled until all required fields are filled.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 13
Issue: Verify redirection to signup page.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. On the login form, locate and click the "Sign up" link or button (usually labeled “Don't have an account?).
3. Observe the URL and page content after clicking.
Env: Production
Module: Login
Priority: P0
Severity: Major
Screenshot:
Expected: Redirects to signup page.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 14
Issue: Verifying reset password with phone number.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Enter phone number reset password field.
3. Click "Submit".
Env: Production
Module: Forgot Password
Priority: P1
Severity: Major
Screenshot:
Expected: A success message is shown; reset password with phone number and redirect reset password
page.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 15
Issue: Ensure Weak Password Handling
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Enter a weak password (e.g., "123").
3. Submit the form.
Env: Production
Module: Forgot Password
Priority: P1
Severity: Major
Screenshot:
Expected: Error shown if password does not meet strength criteria.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 16
Issue: Ensure Redirection to Social Platform Facebook
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Click on the Facebook login button.
3. Confirm redirection to the correct external login page.
Env: Production
Module: Social Login
Priority: P1
Severity: Major
Screenshot:
Expected: Clicking the social login button redirects to the respective platform’s authentication page
(e.g., Google login screen).
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 17
Issue: Verifying Successful Login with Social Account (Facebook).
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Enter valid credentials on the social provider's page.
3. Allow necessary permissions.
4. Confirm redirection to user dashboard.
Env: Production
Module: Social Login
Priority: P1
Severity: Major
Screenshot:
Expected: User is logged in and redirected to the website/dashboard.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 18
Issue: Ensure Verify Token Handling (Security).
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Log in via social login.
3. Inspect browser storage or use developer tools.
4. Ensure token is not exposed in URLs or local storage (if security-critical).
Env: Production
Module: Social Login
Priority: P1
Severity: Major
Screenshot:
Expected: Access token must be stored securely and used for session handling.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 19
Issue: Ensure Logout After Social Login.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/auth/signin
2. Login using a social account.
3. Click logout.
4. Confirm redirection to login page and token/session termination.
Env: Production
Module: Social Login
Priority: P1
Severity: Major
Screenshot:
Expected: User should be logged out from the application, but not necessarily from the social provider.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 20
Issue: Ensure Add Product While Not Logged In.
Reproducing Steps:
1. Go to the URL https://eonbazar.com
2. Log out of the account (if logged in).
3. Add product to cart.
4. View cart and confirm presence.
Env: Production
Module: Add to Cart
Priority: P1
Severity: Major
Screenshot:
Expected: Product is added to a guest session cart.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 21
Issue: Ensure Add Product with Maximum Quantity Limit.
Reproducing Steps:
1. Go to the URL https://eonbazar.com
2. Open product detail page.
3. Try adding quantity beyond the limit.
4. Check for error or warning message.
Env: Production
Module: Add to Cart
Priority: P1
Severity: Major
Screenshot:
Expected: System prevents user from exceeding max quantity (e.g., 10 items).
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 22
Issue: Ensure Guest Checkout Process.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/shop
2. Add an item to the cart.
3. Proceed to checkout without logging in.
4. Fill in shipping and payment details.
5. Confirm and place the order.
Env: Production
Module: Product Checkout
Priority: P1
Severity: Major
Screenshot:
Expected: Guest users can complete the checkout without account creation, providing necessary shipping
and payment information.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 23
Issue: Ensure Order Confirmation Email.
Reproducing Steps:
1. Go to the URL https://eonbazar.com/shop
2. Add an item to the cart.
3. Proceed to checkout without logging in.
4. Fill in shipping and payment details.
5. Confirm and place the order.
Env: Production
Module: Product Checkout
Priority: P1
Severity: Major
Screenshot:
Expected: User receives an order confirmation email with order details after successful checkout.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 24
Issue: Ensure Filter by (Rating high to low & low to high).
Reproducing Steps:
1. Go to the URL https://eonbazar.com
2. On the sidebar, locate the “Tags” or “Attributes” section (e.g., “Frozen,” “Antibiotic-free”).
3. Click on one of the Rating hight to low or low to high.
4. Verify the listed products have that specific tag/attribute.
Env: Production
Module: Filter Product
Priority: P1
Severity: Major
Screenshot:
Expected: Products with the Rating High to low & low to high are displayed.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 25
Issue: Ensure Pagination Within a Category.
Reproducing Steps:
1. Go to the URL https://eonbazar.com
2. Go to a category with many products (if available).
3. Scroll down and click page 2.
4. Ensure additional products load correctly and remain within that category.
Env: Production
Module: Product Category
Priority: P2
Severity: Major
Screenshot:
Expected: Products within a category are paginated correctly if there are more items than fit one page.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 26
Issue: Ensure homepage layout adapts to different screen sizes.
Reproducing Steps:
1. Go to the URL https://eonbazar.com
2. Open browser developer tools (F12).
3. Switch to device toolbar (toggle responsive mode).
4. Select screen sizes:
5. 320x480 (Mobile)
6. 768x1024 (Tablet)
7. 1366x768 (Desktop)
8. Reload the page on each size.
Env: Production
Module: Product Category
Priority: P3
Severity: Major
Screenshot: https://prnt.sc/YC8QJae25Qyu
Expected:
1. Layout adapts fluidly without horizontal scroll.
2. No content overlaps or breaks.
3. Text and buttons remain readable.
Responsible QA: Abdullah Al Omar
Bug Reporting
#SL 27
Issue: Ensure layout adapts to portrait and landscape.
Reproducing Steps:
1. Go to the URL https://eonbazar.com
2. Open on a mobile or tablet.
3. Switch between portrait and landscape
Env: Production
Module: Product Category
Priority: P3
Severity: Major
Screenshot: https://prnt.sc/SpdlyvsbP7Kl
Expected:
1. Layout readjusts properly.
2. No elements are cut off or misaligned.
Responsible QA: Abdullah Al Omar

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Eonbazar.
Module Name | Category functionality,User authentication,User registration |  |  |  |  | Total No. | Status | New Features:- | Testing Scope:-
Feature Name | Register Account ,Account Login,Transaction Functionality, Search Functionality
Test Case Version | 1 |  |  |  |  | 58 | PASS
Written By | Mamun Ali |  |  |  |  | 27 | FAIL
Executed By | Mamun Ali |  |  |  |  | 7 | Not Executed
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 58 | 27 | 7 | 0 | 92
Grand Total | 58 | 27 | 7 | 0 | 92
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (82/82)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/82)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (66/82)*100 = 80.5%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (16/82)*100 = 19.5%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/82)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A